## Sheet1
LEADERSHIP - FSS Adaptation Checklist
Adaptation |  | Type | Status | Owner | Facilitation & Course Delivery |  | Type | Status | Owner
x | Elements Adaptation Guide |  |  | Tysa | x | Survey | doc and pdf
Open | Course User FAQs | pdf | OPEN: We need blurb for LEAD in both sections of what are outcomes and what is next in series. <NEED SOURCE FILE> | Alison | x | Facilitation Guide | doc and pdf
x | Software Requriments | jpg |  |  | x | Online Facilitation Script | doc
In Progress | Resources List | xls |  | Tysa/Stef | x | FG Online Resources (Survey, Discussion Checklist, Discussion Suggestions, Assessment, Facilitator Checklist, Set-up Profile) | zip
x | Adaptation Process | doc |  |  | In Progress | Web Content Scripts | doc | Waiting for final extraction | Julia/Laurye
N/A | Instruments | xls |  |  | In Progress | Web Content Scripts w/ Facilitation | doc | Waiting for final extraction | Julia/Laurye
Elements Course Files |  | Type | Status | Owner | Image Trackers |  | Type | Status | Owner
Pending | Overview Word Counts | Text | Can update once all extractions are delivered | Tysa | Open | Photo Tracker (Props, Photos, Screenshots) | xls
In Progress | Glossary | xls | Need to do final cross-reference with final course LEAD terms | Tysa | Open | Phtoto Tracker Contact Sheets (HighRes per Module) | pdf
In Progress | File Translation List | xls | Need final widget title names from CAMP extraction | Tysa | Open | Source Files for Screenshots | mix
In Progress | Animated Demo Scripts | zip | Need verification from Julia | Tysa
Open | Previews of Demos | htm | Need to create demos | Laurye
x | Animated Demo Instructions | pdf |  | Tysa
Course Content Scripts |  | Type | Status | Owner | Audio and Voice Over |  | Type | Status | Owner
Pending | E-learning Module Content | xml | Waiting for CAMP extraction | Tysa/Laurye | Pending | Audio File List | xls | Waiting for Extraction | Tysa/Laurye
Pending | E-learning LEAD_Structure | doc | Waiting for CAMP extraction | Tysa/Laurye | In Progress | VO Scripts | doc | Waiting for Extraction to cross-reference | Tysa
x | User Interface | doc | CAMP |  | x | VO Instructions | doc
x | Content Script Instructions | doc | CAMP |  | x | Audio MP3s | mp3
x | Sample Content Script | jpg | CAMP
Course Resources |  | Type | Status | Owner | Marketing |  | Type | Status | Owner
x | Action Plans | zip |  | Tysa |  | Elements Flyer | pdf |  | Alison
x | Module Resources | zip |  | Tysa | x | Elements PPT | ppt
x | Additional Resources | mix |  | Tysa |  | CD Production Files | zip
In Progress | Engage Community Info | pdf | Should this also be translated? If so, need source file | Alison |  | (DVD case cover, Insert, CD faceplate)
[5 empty] | Corrections & Updates to Content |  | Type | Status | Owner
[5 empty] | Open | Corrections_LEAD | doc
Note on B5: Fennern, TysaX C: http://download.intel.com/education/common/en/resources/Elements/PBL/FAQs.pdf